## Instructions
Oracle Fusion Impact Analyzer — Enterprise Edition
Purpose | This workbook supports Oracle Fusion quarterly release impact assessment, governance, migration, testing, integration lineage, and operational readiness.
How to use
1. Clients | Register each client or business unit being assessed.
2. Oracle_Releases | Record Oracle quarterly releases to be assessed.
3. Release_Changes | Populate or import Oracle release note changes.
4. Business_Processes | Register in-scope business processes per module.
5. Applications | List all applications and integrations in scope.
6. Configurations | Document key configuration items that may be impacted.
7. Customizations | List customizations, extensions, and CEMLI objects.
8. Controls | Register SOX or operational controls to be re-tested.
9. Test_Cases | Maintain the test case library linked to release changes.
10. Impact_Assessments | Core analysis table. Risk scores are calculated automatically via formula. Set Client_ID and Release_ID to filter the Executive Summary.
11. Remediation_Actions | Track remediation tasks arising from impact assessments.
12. RAID_Log | Log Risks, Assumptions, Issues, and Dependencies.
13. Testing_Command_Centre | Track test execution runs and defect links.
14. Defect_Analytics | Categorise and analyse defects found during testing.
15. Release_Readiness | Record go/no-go readiness status per domain.
16. Integration_Topology | Map all integration connections and their criticality.
17. OTBI_Inventory | Inventory of OTBI reports that may be affected by changes.
18. BIP_Reports | Inventory of BI Publisher reports in scope.
19. HDL_FBDI_Loads | Track HCM Data Loader and FBDI file-based load jobs.
20. Security_Roles | Document Oracle security roles and access levels.
21. Environment_Promotions | Track promotion history across environments.
22. Cutover_Runbook | Step-by-step cutover sequence for go-live.
23. AI_Governance | Govern AI models used in analysis — approval and audit log.
24. Approval_Workflow | Record approval decisions for governed artefacts.
25. Deployment_Status | Track deployment status of components per release.
26. Executive_Summary | Dashboard with KPI counts and risk distribution chart. Enter Client_ID in B3 and Release_ID in B4 to filter.
Governed sheets | Reference_Lists, Scoring_Rules, Metadata_Config, Data_Lineage, and PowerQuery_Control are protected. Contact the workbook owner to amend them.
Support | Internal enterprise use only. Confidential.

## Clients
Client_ID | Client_Name | Client_Code | Industry | Region | Primary_Contact | Support_Model | Risk_Profile | Status
CLT_DEMO01 | Acme Corporation | ACME | Manufacturing | EMEA | Jane Smith | Managed Service | High | Active
CLT_DEMO02 | Beta Retail Ltd | BETA | Retail | APAC | John Lee | Support Only | Medium | Active
CLT_DEMO03 | Gamma Health NHS | GAMMA | Healthcare | UK | Sarah Jones | Managed Service | Critical | Active

## Oracle_Releases
Release_ID | Release_Name | Release_Year | Release_Quarter | Oracle_Product | Release_Date | Notes_Source_URL | Ingestion_Date | Status
REL_24Q3 | Oracle Fusion 24C | 2024 | Q3 | ERP | 2024-09-20 | https://www.oracle.com/readiness | 2026-07-16 | Active
REL_24Q4 | Oracle Fusion 24D | 2024 | Q4 | HCM | 2024-12-20 | https://www.oracle.com/readiness | 2026-07-16 | Active
REL_25Q1 | Oracle Fusion 25A | 2025 | Q1 | SCM | 2025-03-21 | https://www.oracle.com/readiness |  | Planned

## Release_Changes
Change_ID | Release_ID | Change_Title | Change_Description | Oracle_Module | Feature_Area | Change_Type | Technical_Object | API_Service | Config_Area | Security_Flag | Compliance_Flag | Deprecation_Flag | Required_Action | Oracle_Severity | Effective_Date | Source_Reference | Source_Section
CHG_001 | REL_24Q3 | AP Invoice Validation Enhancement | New validation rules added to AP invoice matching. | Payables | Invoice Processing | Functional | AP_INVOICE_MATCH |  | Invoice Matching | N | N | N | Review matching rules | High | 2024-09-20 | Doc ID 2987654 | Section 3.2
CHG_002 | REL_24Q3 | HCM Global HR REST API Change | Breaking change to /workers endpoint response schema. | HCM | Global HR | Technical |  | HCM REST /workers |  | N | N | N | Update API consumers | Critical | 2024-09-20 | Doc ID 2987700 | Section 7.1
CHG_003 | REL_24Q3 | SCM Inventory Opt-In Feature | New opt-in feature for real-time inventory tracking. | SCM | Inventory | Opt-In |  |  | Inventory Config | N | N | N | Evaluate for adoption | Low | 2024-09-20 | Doc ID 2987810 | Section 12.4

## Business_Processes
Process_ID | Process_Name | Module | Sub_Module | Process_Owner | Criticality | Status
BP_001 | Procure to Pay | Payables | Invoice Matching | AP Manager | Critical | Active
BP_002 | Hire to Retire | HCM | Onboarding | HR Director | High | Active
BP_003 | Order to Cash | Receivables | Billing | AR Manager | High | Active
BP_004 | Record to Report | GL | Period Close | Controller | Critical | Active
BP_005 | Plan to Inventory | SCM | Demand Planning | SCM Manager | Medium | Active

## Applications
App_ID | App_Name | App_Type | Vendor | Version | Environment | Criticality | Status
APP_001 | Oracle Fusion ERP | SaaS | Oracle | 24C | PROD | Critical | Active
APP_002 | Oracle Fusion HCM | SaaS | Oracle | 24C | PROD | Critical | Active
APP_003 | Workday Payroll | SaaS | Workday | 2024.1 | PROD | High | Active
APP_004 | Legacy ERP | On-Premise | SAP | ECC 6 |  | Medium | Decommission

## Interfaces
Interface_ID | Interface_Name | Source_System | Target_System | Direction | Protocol | Frequency | Criticality | Status
INT_001 | ERP to Payroll | Oracle ERP | Workday | Outbound | REST | Daily | High | Active
INT_002 | HCM to AD | Oracle HCM | Active Dir | Outbound | SCIM | Hourly | High | Active
INT_003 | Bank Statements | HSBC | Oracle ERP | Inbound | SFTP | Daily | Critical | Active
INT_004 | Tax Engine | Oracle ERP | Vertex | Bidirect | SOAP | RT | Medium | Active

## Jobs_Batches
Job_ID | Job_Name | Schedule | Module | Run_As_User | Criticality | Last_Run_Date | Status
JOB_001 | AP Payment Run | Weekly Mon 02:00 | Payables | AP_BATCH | Critical | 2024-09-16 | Active
JOB_002 | GL Period Close | Monthly EOM | GL | GL_CLOSE | Critical | 2024-08-31 | Active
JOB_003 | HCM Payroll Interface | Bi-weekly Fri | HCM | HCM_PAY | High | 2024-09-13 | Active
JOB_004 | Inventory Reorder | Daily 06:00 | SCM | SCM_INV | Medium | 2024-09-16 | Active

## Environments
Env_ID | Env_Name | Env_Type | Oracle_Product | URL | Refresh_Cadence | Owner | Status
ENV_001 | Production | PROD | Oracle Fusion | https://prod.example.com | Quarterly | IT Ops | Active
ENV_002 | UAT | UAT | Oracle Fusion | https://uat.example.com | Monthly | QA Lead | Active
ENV_003 | Development | DEV | Oracle Fusion | https://dev.example.com | On-demand | Dev Lead | Active
ENV_004 | DR | DR | Oracle Fusion | https://dr.example.com | Quarterly | IT Ops | Active

## Configurations
Config_ID | Module | Config_Area | Config_Name | Config_Value | Last_Changed_Date | Changed_By | Status
CFG_001 | Payables | Invoice Matching | 2-Way Match Tolerance | 5% | 2024-06-01 | AP Manager | Active
CFG_002 | GL | Period Control | Period Close Grace Days | 3 | 2024-01-01 | Controller | Active
CFG_003 | HCM | Absence Management | Max Carry Forward Days | 10 | 2024-04-01 | HR Director | Active
CFG_004 | Payables | Payment Terms | Default Payment Terms | Net30 | 2023-01-01 | AP Manager | Active

## Customizations
Custom_ID | Module | Object_Type | Object_Name | Description | Complexity | Owner | Status
CUS_001 | Payables | Report | AP Ageing Report | Custom AP ageing by supplier | Low | Finance IT | Active
CUS_002 | HCM | Fast Formula | Bonus Eligibility Formula | Determines bonus eligibility | Medium | HR IT | Active
CUS_003 | GL | Workflow | Journal Approval WF | Extended approval routing | Medium | Finance IT | Active
CUS_004 | SCM | Extension | Inventory Valuation Ext | Custom COGS calculation | High | SCM IT | Active

## Controls
Control_ID | Control_Name | Module | Control_Type | Frequency | Owner | Last_Tested_Date | Status
CTL_001 | Segregation of Duties | Payables | SOX | Quarterly | Internal Audit | 2024-06-30 | Active
CTL_002 | Period Close Checklist | GL | Operational | Monthly | Controller | 2024-08-31 | Active
CTL_003 | User Access Review | HCM | SOX | Semi-Annual | Security Team | 2024-06-01 | Active
CTL_004 | Bank Reconciliation | Payables | SOX | Monthly | Treasury | 2024-08-31 | Active

## Test_Cases
Test_Case_ID | Test_Name | Module | Test_Type | Priority | Automation_Flag | Owner | Status
TC_001 | AP Invoice 2-Way Match | Payables | Regression | High | N | QA Team | Active
TC_002 | HCM Worker REST API | HCM | Integration | Critical | Y | QA Team | Active
TC_003 | GL Period Close | GL | Regression | High | N | QA Team | Active
TC_004 | SCM Inventory Opt-In | SCM | UAT | Medium | N | QA Team | Active
TC_005 | Security Role Audit | Security | Compliance | High | N | Security | Active

## Dependencies
Dependency_ID | From_Entity_Type | From_Entity_ID | To_Entity_Type | To_Entity_ID | Dependency_Type | Notes
DEP_001 | Change | CHG_001 | Configuration | CFG_001 | Impacts | Matching tolerance may need review
DEP_002 | Change | CHG_002 | Interface | INT_002 | Breaking | REST schema change breaks HCM-AD sync
DEP_003 | Interface | INT_001 | Job | JOB_003 | Sequence | Payroll job depends on ERP interface

## Scoring_Rules
Rule_ID | Rule_Name | Dimension | Condition | Score | Weight | Effective_Date | Status | Severity_Text | Score
SR_001 | Business Criticality | Business_Criticality_Score | Critical process | 5 | 0.25 | 2024-01-01 | Active | Critical | 5
SR_002 | Business Criticality | Business_Criticality_Score | High priority | 4 | 0.25 | 2024-01-01 | Active | High | 4
SR_003 | Business Criticality | Business_Criticality_Score | Medium priority | 3 | 0.25 | 2024-01-01 | Active | Medium | 3
SR_004 | Business Criticality | Business_Criticality_Score | Low priority | 1 | 0.25 | 2024-01-01 | Active | Low | 1
SR_005 | Customization | Customization_Score | Complex CEMLI | 5 | 0.2 | 2024-01-01 | Active | Informational | 0
SR_006 | Customization | Customization_Score | Simple config | 2 | 0.2 | 2024-01-01 | Active
SR_007 | Integration | Integration_Score | Real-time critical | 5 | 0.15 | 2024-01-01 | Active
SR_008 | Integration | Integration_Score | Batch non-critical | 2 | 0.15 | 2024-01-01 | Active
SR_009 | Security | Security_Score | SOX control | 5 | 0.15 | 2024-01-01 | Active
SR_010 | Environment | Environment_Score | Prod only | 4 | 0.1 | 2024-01-01 | Active

## Impact_Assessments
Assessment_ID | Client_ID | Release_ID | Change_ID | Impact_Type | Impacted_Entity_Type | Impacted_Entity_ID | Impact_Reason | Direct_Match_Flag | Dependency_Match_Flag | Customization_Match_Flag | Security_Impact_Flag | Business_Criticality_Score | Customization_Score | Integration_Score | Security_Score | Environment_Score | Oracle_Change_Score | History_Score | Total_Risk_Score | Risk_Level | Review_Status | Reviewed_By | Review_Date | Recommended_Action | Test_Required_Flag | Remediation_Required_Flag
ASMT_001 | CLT_DEMO01 | REL_24Q3 | CHG_001 | Functional | Configuration | CFG_001 | AP matching rules changed | Y | N | N | N | 4 | 2 | 0 | 0 | 3 |  | 3 |  |  | Pending Review |  |  | Review and update config | Y | Y
ASMT_002 | CLT_DEMO01 | REL_24Q3 | CHG_002 | Technical | Interface | INT_002 | REST API schema breaking change | Y | N | N | N | 5 | 0 | 5 | 0 | 3 |  | 4 |  |  | Pending Review |  |  | Update integration consumer | Y | Y
ASMT_003 | CLT_DEMO01 | REL_24Q3 | CHG_003 | Functional | Configuration | CFG_002 | Opt-in feature — no mandatory action | N | N | N | N | 2 | 0 | 0 | 0 | 1 |  | 1 |  |  | Approved | SCM Manager | 2024-09-22 | Monitor | N | N
Note on A1: Enterprise Oracle Fusion quarterly impact analysis table.

## Remediation_Actions
Action_ID | Assessment_ID | Action_Description | Action_Type | Owner | Due_Date | Priority | Status
ACT_001 | ASMT_001 | Update AP matching config to align with new validation rules | Configuration | AP Manager | 2024-10-15 | High | Open
ACT_002 | ASMT_002 | Update HCM-AD integration to handle new REST schema | Technical | Integration Lead | 2024-10-01 | Critical | In Progress
ACT_003 | ASMT_003 | Evaluate SCM inventory opt-in feature for adoption | Functional | SCM Manager | 2024-11-01 | Low | Open

## Executive_Summary
Oracle Fusion Impact Analyzer Dashboard
Selected Client_ID | Total Impacted Items
Selected Release_ID | Critical Risks

## Review_Log
Review_ID | Entity_Type | Entity_ID | Reviewer | Review_Date | Decision | Comments | Status
REV_001 | Impact_Assessment | ASMT_001 | Jane Smith | 2024-09-25 | Approved | Reviewed and accepted | Approved
REV_002 | Impact_Assessment | ASMT_002 | John Lee | 2024-09-26 | Rejected | Needs more detail | Rejected
REV_003 | Design_Decision | DD_001 | CTO | 2024-09-20 | Approved | Approved for 24C | Approved

## Reference_Lists
Modules | RiskLevels | Statuses | YesNo | ReviewStatus
Payables | Low | Draft | Y | Pending Review
Receivables | Medium | Active | N | Approved
Procurement | High | Inactive |  | Rejected
GL | Critical | Approved
Projects |  | Rejected
SCM
HCM

## Metadata_Config
Generated_Date | 2026-07-16 14:09:51
Workbook_ID | f9dbd76e-8c68-4dc0-ab40-19d7b54ac231
Version | 1.0

## PowerQuery_Control
Query_Name | Layer | Depends_On | Refresh_Order | Owner | Active
qry_clients | Bronze |  | 1 | Data Engineer | Y
qry_release_changes | Bronze |  | 2 | Data Engineer | Y
qry_impact_silver | Silver | qry_clients | 3 | Data Engineer | Y
qry_dashboard | Gold | qry_impact_silver | 4 | BI Lead | Y

## Data_Lineage
Source_System | Source_Object | Source_Field | Transformation_Rule | Target_Table | Target_Field
Oracle HCM | PER_ALL_PEOPLE_F | PERSON_ID | Direct copy | W_PERSON_D | PERSON_WID
Oracle ERP | AP_INVOICES_ALL | INVOICE_AMOUNT | Convert to USD | W_AP_INVOICE_F | INVOICE_AMT_USD
Oracle SCM | MTL_SYSTEM_ITEMS_B | UNIT_COST | Multiply by quantity | W_INVENTORY_F | EXTENDED_COST

## Refresh_Audit
Execution_ID | Timestamp | Executed_By | Rows_Processed | Exceptions_Found | Execution_Status
EXEC_001 | 2024-09-20 08:00:00 | Data Engineer | 1250 | 3 | Success
EXEC_002 | 2024-09-21 08:00:00 | Data Engineer | 1302 | 0 | Success
EXEC_003 | 2024-09-22 08:00:00 | Scheduled Job | 1298 | 1 | Warning

## Exceptions_Unmapped_Modules
Exception_Type | Record_ID | Description | Detected_Date

## Exceptions_Missing_Criticality
Exception_Type | Record_ID | Description | Detected_Date

## Exceptions_Invalid_Status
Exception_Type | Record_ID | Description | Detected_Date

## Exceptions_Duplicate_IDs
Exception_Type | Record_ID | Description | Detected_Date

## Requirements_Traceability
Req_ID | Requirement_Name | Module | Design_ID | Test_Case_ID | Defect_ID | Status
REQ_001 | AP Matching Tolerance Config | Payables | DD_002 | TC_001 |  | Active
REQ_002 | HCM REST API Integration | HCM | DD_003 | TC_002 | DEF_001 | Active
REQ_003 | SCM Inventory Real-Time Track | SCM | DD_004 | TC_004 |  | Active

## Fit_Gap_Assessment
FitGap_ID | Process_ID | Requirement | Oracle_Coverage | Gap_Description | Resolution_Type | Priority | Status
FG_001 | BP_001 | 3-Way PO Match | Partial | Native only supports 2-way | Configuration | High | Open
FG_002 | BP_002 | Custom Bonus Calculation | Gap | No standard formula equivalent | Extension | Medium | Resolved
FG_003 | BP_004 | Multi-currency Revaluation | Fit | Fully covered by Oracle standard | None | Low | Closed

## Design_Decisions
Decision_ID | Module | Decision_Title | Decision_Description | Rationale | Decision_Owner | Decision_Date | Status
DD_001 | Payables | Invoice Matching Strategy | Use Oracle native 2-way match with custom tolerance | Minimise customisation risk | Solution Architect | 2024-08-01 | Approved
DD_002 | HCM | REST API Versioning Strategy | Pin integration to v22 REST API; migrate to v24 post-upgrade | Reduce upgrade risk | Integration Architect | 2024-08-15 | Approved
DD_003 | SCM | Inventory Opt-In Adoption | Defer real-time inventory opt-in to 25A release cycle | Insufficient testing time in 24C window | SCM Lead | 2024-09-01 | Approved

## OTBI_Inventory
Report_ID | Subject_Area | Owner | Criticality | Security_Role | Last_Reviewed
OTB_001 | Payables - Invoices | AP Manager | Critical | AP_REPORT_ROLE | 2024-06-01
OTB_002 | HCM - Workforce Summary | HR Director | High | HCM_REPORT_ROLE | 2024-06-01
OTB_003 | GL - Trial Balance | Controller | Critical | GL_REPORT_ROLE | 2024-06-01
OTB_004 | SCM - Inventory Ageing | SCM Manager | Medium | SCM_REPORT_ROLE | 2024-06-01

## BIP_Reports
Report_ID | Report_Name | Module | Owner | Criticality | Security_Role | Last_Reviewed | Status
BIP_001 | AP Payment Remittance | Payables | AP Manager | Critical | AP_REPORT_ROLE | 2024-06-01 | Active
BIP_002 | Payslip Report | HCM | HR Director | High | HCM_REPORT_ROLE | 2024-06-01 | Active
BIP_003 | GL Journal Report | GL | Controller | High | GL_REPORT_ROLE | 2024-06-01 | Active

## HDL_FBDI_Loads
Load_ID | Object_Name | Load_Type | Validation_Status | Rejected_Records | Source_File | Last_Load_Date
LOAD_001 | Worker | HDL | Validated | 0 | workers_20240901.dat | 2024-09-01
LOAD_002 | Salary | HDL | Validated | 2 | salary_20240901.dat | 2024-09-01
LOAD_003 | Supplier | FBDI | Validated | 0 | suppliers_20240901.xlsx | 2024-09-01
LOAD_004 | Journal Entries | FBDI | Rejected | 45 | journals_20240902.xlsx | 2024-09-02

## Security_Roles
Role_ID | Role_Name | Module | Role_Type | Data_Access_Level | Last_Reviewed | Owner | Status
ROL_001 | AP Manager | Payables | Job | Restricted | 2024-06-01 | Finance | Active
ROL_002 | AP Supervisor | Payables | Job | Full | 2024-06-01 | Finance | Active
ROL_003 | HR Analyst | HCM | Job | Restricted | 2024-06-01 | HR Ops | Active
ROL_004 | IT Security Admin | Security | Abstract | Full | 2024-06-01 | IT Security | Active

## Environment_Promotions
Promotion_ID | Release_ID | From_Env | To_Env | Promotion_Date | Promoted_By | Approval_Status | Notes
PROM_001 | REL_24Q3 | DEV | UAT | 2024-09-10 | Dev Lead | Approved | Initial UAT deploy
PROM_002 | REL_24Q3 | UAT | PROD | 2024-09-20 | IT Ops | Approved | Go-live deploy 24C
PROM_003 | REL_24Q4 | DEV | UAT |  |  | Pending | Planned for Nov 2024

## Cutover_Runbook
Step_ID | Step_Name | Responsible_Team | Estimated_Duration | Dependencies | Rollback_Procedure | Status
STEP_001 | Freeze ERP Transactions | Finance Ops | 2h |  | Resume from backup point | Complete
STEP_002 | Run Final HDL Loads | IT Ops | 3h | STEP_001 | Re-run load files | Complete
STEP_003 | Execute Smoke Tests | QA Team | 4h | STEP_002 | Rollback to STEP_001 | Complete
STEP_004 | Go / No-Go Decision | Steering | 1h | STEP_003 | Invoke rollback plan | Complete
STEP_005 | Open System to Users | IT Ops | 1h | STEP_004 | Emergency freeze | Complete

## Testing_Command_Centre
Test_Run_ID | Release_ID | Test_Case_ID | Execution_Status | Defect_Link | Automation_Status | Executed_By | Execution_Date
TRN_001 | REL_24Q3 | TC_001 | Passed |  | Manual | QA Team | 2024-09-12
TRN_002 | REL_24Q3 | TC_002 | Failed | DEF_001 | Manual | QA Team | 2024-09-12
TRN_003 | REL_24Q3 | TC_003 | Passed |  | Automated | QA Team | 2024-09-13
TRN_004 | REL_24Q3 | TC_004 | Blocked |  | Manual | QA Team | 2024-09-13
TRN_005 | REL_24Q3 | TC_005 | Passed |  | Manual | Security | 2024-09-14

## Defect_Analytics
Defect_ID | Release_ID | Severity | Root_Cause | Assigned_Team | Duplicate_Group | Status
DEF_001 | REL_24Q3 | Critical | Integration Schema Change | Integration Team |  | Open
DEF_002 | REL_24Q3 | Medium | Config Regression | AP Team | GRP_001 | Resolved
DEF_003 | REL_24Q3 | Low | UI Label Mismatch | QA Team |  | Closed

## RAID_Log
RAID_ID | Type | Description | Impact | Owner | Due_Date | Status
RAID_001 | Risk | HCM REST API breaking change may delay go-live | Integration downtime | Integration Lead | 2024-10-01 | Open
RAID_002 | Issue | DEF_001 unresolved — HCM-AD sync failure | HR data not syncing | QA Team | 2024-09-25 | Open
RAID_003 | Assumption | Oracle 24C released on schedule 20-Sep-2024 | Low | PM | 2024-09-20 | Closed
RAID_004 | Dependency | Workday Payroll upgrade must align with HCM 24C | Payroll gap risk | HR Director | 2024-10-15 | Open

## Release_Readiness
Domain | Testing_Complete | Defects_Open | Critical_Risks | Deployment_Ready
ERP / Finance | Y | 0 | 0 | Y
HCM | N | 1 | 1 | N
SCM | Y | 0 | 0 | Y
Security | Y | 0 | 0 | Y
Integration | N | 1 | 1 | N

## Integration_Topology
Integration_ID | Source_System | Target_System | Protocol | Middleware | Criticality | Monitoring_Enabled
INT_001 | Oracle ERP | Workday | REST | Oracle OIC | High | Y
INT_002 | Oracle HCM | Active Dir | SCIM | Oracle OIC | High | Y
INT_003 | HSBC | Oracle ERP | SFTP | Direct | Critical | Y
INT_004 | Oracle ERP | Vertex | SOAP | Oracle OIC | Medium | N

## AI_Governance
Model_Name | Use_Case | Human_Approval_Required | Production_Approved | Validation_Date | Risk_Level | Audit_Required
GPT-4o | Release note summarisation | Y | N | 2024-09-01 | Medium | Y
Watson NLP | Impact classification | Y | N | 2024-09-01 | Medium | Y
Internal LLM | Remediation recommendations | Y | N |  | High | Y

## Approval_Workflow
Approval_ID | Entity_Type | Entity_ID | Approver | Approval_Date | Decision | Comments | Status
APR_001 | Impact_Assessment | ASMT_001 | Finance Director | 2024-09-25 | Approved | Approved for 24C | Approved
APR_002 | Impact_Assessment | ASMT_002 | CTO | 2024-09-26 | Pending |  | Pending
APR_003 | Design_Decision | DD_001 | Solution Arch | 2024-09-20 | Approved | Accepted | Approved

## Deployment_Status
Deployment_ID | Release_ID | Environment | Component | Deployed_By | Deployment_Date | Validation_Status | Notes
DEPL_001 | REL_24Q3 | UAT | ERP Core | IT Ops | 2024-09-10 | Passed | UAT deploy successful
DEPL_002 | REL_24Q3 | UAT | HCM Module | IT Ops | 2024-09-10 | Failed | DEF_001 blocker
DEPL_003 | REL_24Q3 | PROD | ERP Core | IT Ops | 2024-09-20 | Passed | Go-live successful
DEPL_004 | REL_24Q3 | PROD | HCM Module | IT Ops | 2024-09-21 | Passed | Post-fix deploy